## High level features
DATAPOLISH FEATURES & IMPLEMENTATION REQUIRED
Key Feature | General Summary | Technical elements required (e.g., ML, api call) | Related documentation | Epic Jira | Other comments
Data Preview V1 | The page after data import. The data preview will show the user a preview of their data to ensure correct importation. This is a key feature that exits in almost all competitors. Some competitors such as open refine and Dblist allow user to complete actions that impact the whole dataset, such as selecting primary key if applicable. | UI, Python/Java, API call | Requirements doc | FAB-196 | May include other technical elements. ASD input required.
Data Import V2 | Feature to import data. Version 1 only allows comma delimited csv files with data with col headings on the first row and data from the second row. Version 2 will allow all csv files and one sheet excel files. | UI, Python/Java, API call | Requirements doc | FAB-200 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Current profiling feature is static pyplots. The interactive data profile dashboard will be interactive and live on a web page post data preview to allow the user to gauge the status of their data. Version 2 will include profiling visuals, data quality visuals, a user feedback feature and engagement tracking of the user. A tool tip for each visual | UI, python, javascript, D3.js, API call, java | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Current data cleaning only does dataset level data cleaning actions. This feature performs column level actions, such as imputing missing data in a field or normalising the data. | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Interactive data profile dashboard V2 | Version 2 will include some "exciting" features requested by the user, in expert feedback and competitor research. Including advanced statistical charts, chart annotation, exporting data of visuals, a history log and an educational feature. | UI, python, javascript, D3.js, API call, java | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Column specific cleaning version 2 | Include some complex features such as creating calculated fields or dimensional reduction techniques using ML. | UI, python, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Data Export V2 | User can specify whether they want to export to excel or csv, the user can also revert back to profiling to check the DQ of their newly clean data and start that part of the workflow again. | UI, python, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Data Import V3 | User can import multiple files of the same structure and type and have them unioned if they specify. User can also import JSON | UI, python, API call | TBC | TBC | Not selected for priority by December, subject to change. Highlighted for future work
Data Preview V2 | Dimension reduction for highdimensional datasets to solve for edge case of datasets with 100+ cols | UI, python, API call | TBC | TBC | Not selected for priority by December, subject to change. Highlighted for future work
Column specific cleaning version 3 | Solve for multiple instances within a single instance and ability to pivot dataset. | UI, python, API call | TBC | TBC | Not selected for priority by December. Highlighted for future work
Interactive data profile dashboard V3 | Export selected visuals. Implement data rule validation which highlights fields where the custom rule has been broken. | UI, python, javascript, D3.js, API call, java | TBC | TBC | Not selected for priority by December. Highlighted for future work
Data Export V3 | Ability to export to mutliple file types, to export to a database or export the dataframe straight into colab. |  | TBC | TBC | Not selected for priority by December. Highlighted for future work
Data analysis V1 | More research required but similar to competitor analysis tool, such as oracle, alteryx and orange. Allow users to select fields to analyse. Think augmented analytics in excel, tableau and power BI |  | TBC | TBC | Not selected for priority by December. Highlighted for future work
LLM | Allow the user to ask questions of their data in natural language post cleaning. |  | TBC | TBC | Not selected for priority by December. Highlighted for future work
Data Cleaning cross datasets (ETL) | ETL functionality with joins to alternative datasets. ETL functionality with joins to alternative datasets. User can import a separate dataset |  | TBC | TBC | Not selected for priority by December. Highlighted for future work

## Timeline
Week No | Week | Features to be included | Comments | Week No | Week start | Week end | Days taken | Section | Team | Features
2 | 25th - 29th Sep | Data Import | Start of work and research | 2 | 2023-09-25 | 2023-10-01 | 5 | MVP | ASD | Data import
3 | 2nd - 6th Oct | Data Quality checks and export of data | Data quality check module created, not all functions made it to final | 2 | 2023-09-25 | 2023-10-08 | 10 | MVP | DS | Research
4 | 9th-13th Oct | Data cleaning | Data cleaning module created, only dataset wide cleaning uptaken | 2 | 2023-09-25 | 2023-10-29 | 25 | MVP | ASD | UI
5 | 16th - 20th Oct | Data Profiling images | D3 dashboard scrapped for this release, only static pyplots | 2 | 2023-09-25 | 2023-10-29 | 25 | MVP | ASD | Backend
6 | 23rd - 27th Oct | UI imporvements and stability | Worked on stability | 2 | 2023-09-25 | 2023-10-29 | 25 | MVP | ASD/DS | Intergration
7 | 30th - 3rd Nov | Data Preview and Data Import V2 | Data preview to be finished | 3 | 2023-10-02 | 2023-10-08 | 5 | MVP | DS | DQ checks
8 | 6th - 10th Nov | Data profile dashboard and data cleaning column level | D3 dashboard and column level cleaning | 3 | 2023-10-02 | 2023-10-08 | 5 | MVP | DS | Data clean
9 | 13th - 17th Nov | Create new columns, Dimension reduction | Not finalised but more complex features to be released | 4 | 2023-10-09 | 2023-10-13 | 5 | MVP | ASD | Data export
10 | 20th - 24th Nov | Statistical analysis data profile visuals and annotation | More complex charts in data profiling | 4 | 2023-10-09 | 2023-10-22 | 5 | MVP | DS | Data profiling
11 | 27th - 1st Dec | Multiple file imports | Allow users to upload multiple files | 5 | 2023-10-16 | 2023-10-22 | 5 | MVP | DS | Python integration
12 | 4th - 8th Dec | Testing and evaluation | Small improvements or possible new functionality | 6 | 2023-10-23 | 2023-10-29 | 5 | MVP | DS | Testing
13 | 11th - 15th Dec | Testing and evaluation | Stop all functionality | 7 | 2023-10-30 | 2023-11-05 | 5 | Beta | ASD | Data import v2
14 | 18th - 22nd Dec | Final report writing and presentation | Product stable and general release. | 7 | 2023-10-30 | 2023-11-05 | 5 | Beta | ASD | Data preview
|  |  |  | 7 | 2023-10-30 | 2023-11-12 | 10 | Beta | DS | D3 profile dashboard
|  |  |  | 7 | 2023-10-30 | 2023-11-12 | 10 | Beta | DS | Column cleaning
|  |  |  | 7 | 2023-10-30 | 2023-11-12 | 10 | Beta | ASD | Col clean UI
|  |  |  | 8 | 2023-11-06 | 2023-11-12 | 5 | Beta | ASD | D3 dash Intergration
|  |  |  | 9 | 2023-11-13 | 2023-11-19 | 5 | Beta | ASD/DS | Test and user feedback
|  |  |  | 9 | 2023-11-13 | 2023-11-26 | 10 | Alpha | DS | Advanced D3
|  |  |  | 9 | 2023-11-13 | 2023-11-26 | 10 | Alpha | DS | Advanced col clean
[5 empty] | 2023-11-27 | 2023-12-17 | 15 | Alpha | ASD/DS | Testing
[5 empty] | 2023-11-27 | 2023-12-17 | 15 | Alpha | ASD/DS | Evaluation
[5 empty] | 2023-11-27 | 2023-12-17 | 15 | Alpha | ASD/DS | User feedback
[5 empty] | 2023-12-18 | 2023-12-24 | 5 | Gen | ASD/DS | General release
[5 empty] | 2023-12-18 | 2023-12-24 | 5 | Gen | ASD/DS | Finalise report

## Sub level features
DATAPOLISH SUB-FEATURES & IMPLEMENTATION REQUIRED
Key Feature | Sub Feature | General Summary | Technical elements required (e.g., ML, api call) | Related documentation | Epic Jira | Other comments
Data Preview V1 | View Sample Data | Post data import the user can view a sample of their data to ensure data importation was correct. | UI, Python/Java, API call | Requirements doc | FAB-196 | May include other technical elements. ASD input required.
Data Preview V1 | Primary Key selection | Allow user to specify their primaryn key if applicable to them. Can be used in DQ checks and cleaning. | UI, Python/Java, API call | Requirements doc | FAB-196 | May include other technical elements. ASD input required.
Data Preview V1 | Target analysis variable selection | DS students typically work with a target variable in mind, this will be used in DQ checks and statistical profiling set for V2 of Data profiling dashboard. | UI, Python/Java, API call | Requirements doc | FAB-196 | May include other technical elements. ASD input required.
Data Import V2 | Allow import of different CSV formats | CSV can come in different formats such as comma, tab or pipe delimeted. V1 only allows comma, we found target users reguarly use different types. | UI, Java, Python, API call | Requirements doc | FAB-200 | May include other technical elements. ASD input required.
Data Import V2 | Allow single sheet excel files | The second most used file type among DS students is excel. This feature allows them to use excel files with single sheet. | UI, Java, Python, API call | Requirements doc | FAB-200 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Display number of records | Display the number of records in the profiling section of dashboard. | UI, python, javascript, D3.js, API call | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Display number of fields | Display the number of fields in the profiling section of dashboard. | UI, python, javascript, D3.js, API call | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Display file name | Display the file name in the profiling section of the dashboard. | UI, python, javascript, D3.js, API call | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Display Data Types of all fields. | Display a count of all data types in the given dataset. Profiling section | UI, python, javascript, D3.js, API call | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Missing values chart | Display the number of missing values in each field. (Bar chart). DQ section | UI, python, javascript, D3.js, API call | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Display number of duplicate records | Show the number of duplicate records and their location (given user PK or row ID). DQ section | UI, python, javascript, D3.js, API call | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Display outliers | Display outliers in the user data using scatter plots. DQ section | UI, python, javascript, D3.js, API call | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Cardinality | Show the number of unique values in each field. Important for DS students to be aware of to tackle the "curse of dimensionality". DQ section | UI, python, javascript, D3.js, API call | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | User feedback functionality | Incorporate simple user feedback to each visual (thumb up for good, thumb down for bad). Recording whether user found the visual useful or not. | UI, python, javascript, D3.js, API call | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Engagement tracking | Incorportate engament tracking, such as google analytics or something. | Google analytics or something else. | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Interactive data profile dashboard V1 | Tool tip for every visual | Incorporate a tool tip for every visual giving extra detail to the user on the visual they are looking at. | UI, python, javascript, D3.js, API call | Requirements doc | FAB-184 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Create UI | The UI needs to fulfill the requirements of the subsequent features listed. Design shown in protoype and documentation. | UI | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Clean null values | Allow user to either remove nulls in a field or impute with statistical techniques. | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Ability to rename columns | Allow user to rename columns | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Ability to select and drop columns | Allow user to select columns for export | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Ability to change data type | Ability to change data type | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Show key DQ metrics for column | When user hovers over column show a tooltip which highlights some DQ metrics, e.g. number of missing values in col. | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Ability to normalise data in a column | Ability to normalise the data in a column using min-max | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Ability to one hot encode a column | Ability to one hot encode a column (catergorical to numeric data) | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Ability to deal with outliers | Impute with mean/median or remove them. | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Special character removal in text fields. | Remove special characters, a big ask from users who are scraping web data. | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Trim white space | Ability to trim white space in a column | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Move column | Abilty for the user to rearrange columns. Switching the index | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Column specific cleaning version 1 | Binning | Ability to change numeric columns into catergorical by binning the numbers into ranges, such as 18-30 etc | UI, python, API call | Requirements doc | FAB-171 | May include other technical elements. ASD input required.
Interactive data profile dashboard V2 | Show distribution plots in advanced statistical analysis | Requested by user in the dashboard to highlight the distribution of their numeric fields. | UI, python, javascript, D3.js, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Interactive data profile dashboard V2 | Show skewness and Kurtois plots in advanced statistical analysis | Requested by user in the dashboard to help determine normality | UI, python, javascript, D3.js, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Interactive data profile dashboard V2 | Show correlation plots in advanced statistical analysis. | Requested by user to show correlation between fields and target variable. | UI, python, javascript, D3.js, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Interactive data profile dashboard V2 | Annotation | Allow the user to annotate charts and make their own notes. Expert feedback requirement. | UI, python, javascript, D3.js, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Interactive data profile dashboard V2 | Export data of visuals | Allow the user to export data from the visuals in dasboard to take a deeper dive. | UI, python, javascript, D3.js, API call, java | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Interactive data profile dashboard V2 | History log | Show users changes between pre cleaned and post cleaned data | UI, python, javascript, D3.js, API call, java | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Interactive data profile dashboard V2 | DQ score | Create a summary score between 1 and 10 giving the user a summary of how clean their data is. | UI, python, javascript, D3.js, API call, java | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Column specific cleaning version 2 | Dimensionality reduction | Allow the user to use ML techniques to reduce the dimensions in a high dimensional column. | UI, python, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Column specific cleaning version 2 | Create new calculated fields | Allow the user to create calculated fields from existing fields in the dataset. | UI, python, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Column specific cleaning version 2 | Preset features | If existing user and user is using a similar dataset (year 2) they can select run data clean using the same features from the last time. | UI, python, API call, Java | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Data Export V2 | Export to excel | Allow the user to export to an excel file | Java/Python, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Data Export V2 | Revert back to data profiling dashboard post cleaning. | Allow the user to see the data profile dashboard post cleaning to see the new status of their data | UI, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Data Export V2 | Show DQ score | Show the DQ score of the newly cleaned data before exporting | UI, API call | TBC | TBC | Selected as part of priority for December release but sub-level features may change priority based on user feedback and limited timing
Data Import V3 | Multiple file imports | Allow the user to import multiple files of the same structure and type which unions them. | UI, Java, Python, API call | TBC | TBC | Not priority for December release, possible future work.
Data Import V3 | Remove meta data | At times datasets can contain metadata in the first x rows, allow user to capture meta data and specify where the data starts. (edge case) | UI, Java, Python, API call | TBC | TBC | Not priority for December release, possible future work.
Data Import V3 | Excel multiple sheets | Allow user to import multiple sheets from an excel file | UI, Java, Python, API call | TBC | TBC | Not priority for December release, possible future work.
Data Import V3 | JSON files | Allow user to import json files | UI, Java, Python, API call | TBC | TBC | Not priority for December release, possible future work.
Data Preview V2 | Edge case of extreme dimensionality | An edge case where the user has 50+ fields may make the web app redundant. Some sort of solution to perform PCA for the user or another dimension reduction technique. | UI, Java, Python, API call | TBC | TBC | Not priority for December release, possible future work.
Column specific cleaning version 3 | Expand records with multi instances | At times records can have multiple instances within one record instances. The data in this needs to be in a structured fromat for DS student to analyse | UI, Java, Python, API call | TBC | TBC | Not priority for December release, possible future work.
Column specific cleaning version 3 | Pivot table | Allow the user to create a pivot table | UI, Java, Python, API call | TBC | TBC | Not priority for December release, possible future work.
Interactive data profile dashboard V3 | Data rule validation | Allow user to input their own data rule validation which leads to data quality visuals being created highlighting where these rules are violated. | UI, python, javascript, D3.js, API call, java | TBC | TBC | Not priority for December release, possible future work.
Interactive data profile dashboard V3 | Export visuals | Allow the user to export selected visuals so that may be added to their thesis documents. | UI, python, javascript, D3.js, API call, java | TBC | TBC | Not priority for December release, possible future work.
Interactive data profile dashboard V3 | Filters and parameters | Add filters and parameter selction to the dashboard. Such as only selecting columns they want to see. | UI, python, javascript, D3.js, API call, java | TBC | TBC | MAY CHANGE TO VERSION 2. COULD BE A MUST REQUIREMENT DEPENDING ON USER FEEDBACK
Data Export V3 | Export to databases | Allow the user to set up connections to external relational databases to export to. | UI, Java, Python, API call | TBC | TBC | Not priority for December release, possible future work.
Data Export V3 | Connect to Collab | Export the data straight into collab which is the primary analysis platform for our target users. (Nice to have) | UI, Java, Python, API call | TBC | TBC | MAY CHANGE TO VERSION 2. COULD BE A MUST REQUIREMENT DEPENDING ON USER FEEDBACK. Not a must but a nice to have.
Data analysis | Allow user to select fields they want analysed. | Similar to competitor analysis tool, such as oracle, alteryx and orange. |  | TBC | TBC | Not priority for December release, possible future work.
LLM | Allow the user to ask questions of their data in natural language post cleaning. | Think of Panda AI but custom made. |  | TBC | TBC | Not priority for December release, possible future work.
Data Cleaning cross datasets (ETL) | ETL functionality with joins to alternative datasets | ETL functionality with joins to alternative datasets. User can import a separate dataset | UI, Java, Python, API call | TBC | TBC | Not priority for December release, possible future work.